## Start here
Open PO Health Check
Find late, stuck and at-risk purchase orders in about 10 minutes.
How to use it
1. Settings | Today's date fills itself in. Change the at-risk window or the 'stale' threshold if your lead times are unusual.
2. Open POs | Delete the 12 sample rows (rows 5 to 16), then paste one row per open PO line (one SKU per row). Fill the cream-coloured columns A to N. The grey columns O to V calculate themselves.
3. Dashboard | Updates automatically: how many lines are late, overdue to ship, at risk or silent, and how much money is tied up in them.
4. Supplier scorecard | Type your supplier names in column A exactly as they appear in Open POs. Each supplier's late lines and longest silence fill in.
5. Follow-up templates | Copy the message that matches the line's Health, fill the {brackets}, and send. Each comes in English and Simplified Chinese.
Colour legend
Cream cells | You type here.
Grey cells | Formulas. Don't type over them; copy them down if you add more than 200 lines.
What each Health label means
Late | The promised arrival date (ETA) has passed and the line isn't received.
Ship overdue | The promised ship date has passed and the status isn't Shipped yet.
At risk | Status is Delayed, or the ETA is within the at-risk window and it hasn't shipped.
Stale | No update from the supplier for longer than the stale threshold.
On track | None of the above.
Closed | Status is Received, or everything ordered has been received.
Stockout column | If you add units on hand and average daily sales, column U warns when your stock runs out before the promised ETA, and by how many days.
Made by Ordersmithy ¦ ordersmithy.com ¦ hello@ordersmithy.com

## Settings
Settings
Change the cream cells if you need to. Every other sheet reads from here.
Setting | Value | Notes
Today's date | 2026-10-07 | Updates itself. Type a fixed date here to check the sheet as of another day.
At-risk window (days before ETA) | 10 | Lines arriving within this many days that haven't shipped are flagged At risk. Default 10 days; raise it for long sea freight.
Stale after (days without a supplier update) | 7 | Open lines with no supplier update for longer than this are flagged Stale. Default 7 days.

## Open POs
Open POs
One row per PO line. Cream columns (A to N) are yours to fill. Grey columns (O to V) calculate. Rows 5 to 16 are samples: delete them before adding your own.
YOU TYPE | [13 empty] | CALCULATED
PO # | Supplier | Item / SKU | Channel | Qty ordered | Qty received | Order date | Promised ship date | Promised arrival (ETA) | Last supplier update | Status | PO value ($) | On hand (units, optional) | Avg daily sales (units, optional) | Qty outstanding | Days late | Days since update | Health | Next action | Days of stock cover | Stockout before ETA? | Follow up by
PO-2041 | Supplier A - Ningbo (sample) | SKU-1001 Garlic press | Email | 2000 | 0 | 2026-08-08 | 2026-09-17 | 2026-10-02 | 2026-09-28 | Shipped | 6400 | 150 | 40 | 2000 | 5 | 9 | Late | Ask for a new ETA and tracking number | 3.75 | ETA passed: 4 days of stock left | 2026-10-07
PO-2043 | Supplier B - Shenzhen (sample) | SKU-2010 Silicone lid set | WeChat | 1500 | 0 | 2026-08-18 | 2026-09-22 | 2026-10-05 | 2026-09-25 | Delayed | 4200 | 300 | 25 | 1500 | 2 | 12 | Late | Ask for a new ETA and tracking number | 12 | ETA passed: 12 days of stock left | 2026-10-07
PO-2047 | Supplier A - Ningbo (sample) | SKU-1004 Peeler | Email | 3000 | 0 | 2026-08-28 | 2026-10-04 | 2026-11-01 | 2026-09-27 | In production | 3900 | 500 | 30 | 3000 | 0 | 10 | Ship overdue | Ask why it hasn't shipped; get a firm ship date | 16.6667 | YES: 8 days short | 2026-10-07
PO-2049 | Supplier C - Yiwu (sample) | SKU-3002 Storage jar 1L | WhatsApp | 1200 | 0 | 2026-09-02 | 2026-10-06 | 2026-11-06 | 2026-10-03 | Ready to ship | 5100 | 220 | 20 | 1200 | 0 | 4 | Ship overdue | Ask why it hasn't shipped; get a firm ship date | 11 | YES: 19 days short | 2026-10-07
PO-2052 | Supplier B - Shenzhen (sample) | SKU-2014 Lunch box | WeChat | 1800 | 0 | 2026-09-07 | 2026-10-12 | 2026-10-15 | 2026-10-04 | Confirmed | 5400 | 900 | 20 | 1800 | 0 | 3 | At risk | Confirm the ship date this week | 45 | No | 2026-10-09
PO-2055 | Supplier D - Dongguan (sample) | SKU-4001 Bamboo board | Email | 800 | 0 | 2026-09-09 | 2026-10-10 | 2026-11-16 | 2026-10-05 | Delayed | 7200 | 400 | 10 | 800 | 0 | 2 | At risk | Confirm the ship date this week | 40 | No | 2026-10-09
PO-2058 | Supplier C - Yiwu (sample) | SKU-3005 Spice rack | WhatsApp | 600 | 0 | 2026-09-12 | 2026-10-17 | 2026-11-21 | 2026-09-26 | In production | 3300 | 600 | 8 | 600 | 0 | 11 | Stale | Request a status update | 75 | No | 2026-10-07
PO-2060 | Supplier A - Ningbo (sample) | SKU-1007 Whisk | Email | 2500 | 0 | 2026-09-17 | 2026-10-22 | 2026-11-26 | 2026-10-04 | In production | 2750 | 1200 | 25 | 2500 | 0 | 3 | On track | No action needed | 48 | YES: 2 days short
PO-2063 | Supplier D - Dongguan (sample) | SKU-4003 Knife block | Email | 500 | 0 | 2026-09-22 | 2026-10-27 | 2026-12-01 | 2026-10-06 | Confirmed | 6000 | 700 | 5 | 500 | 0 | 1 | On track | No action needed | 140 | No
PO-2066 | Supplier B - Shenzhen (sample) | SKU-2020 Bottle brush | WeChat | 3000 | 0 | 2026-09-27 | 2026-11-01 | 2026-12-06 | 2026-10-05 | Confirmed | 1800 | 2000 | 30 | 3000 | 0 | 2 | On track | No action needed | 66.6667 | No
PO-2030 | Supplier C - Yiwu (sample) | SKU-3001 Storage jar 500ml | WhatsApp | 1500 | 1500 | 2026-07-09 | 2026-08-18 | 2026-09-22 | 2026-09-21 | Received | 4500 | 800 | 20 | 0 | 15 | 16 | Closed | - | 40
PO-2034 | Supplier A - Ningbo (sample) | SKU-1002 Can opener | Email | 1000 | 1000 | 2026-07-19 | 2026-08-28 | 2026-09-27 | 2026-09-25 | Received | 2300 | 600 | 15 | 0 | 10 | 12 | Closed | - | 40
Formulas:
Follow up by = IF([Health]="","",IF(OR([Health]="Late",[Health]="Ship overdue",[Health]="Stale"),Settings!$B4,IF([Health]="At risk",Settings!$B4+2,"")))
Note on K4: Pick from the list: Confirmed, In production, Ready to ship, Shipped, Delayed, Received.
Note on U4: Compares when your stock runs out (today + days of cover) with the promised ETA. Needs columns M and N.

## Dashboard
Dashboard
As of | 2026-10-07
Key numbers | Value |  | What it tells you
Open PO lines | 10 |  | Lines you are still waiting on.
Money in open POs ($) | 46050 |  | Cash committed to orders not yet received.
Lines late or overdue to ship | 4 |  | Need a supplier follow-up today.
Money in late or overdue lines ($) | 19600 |  | Cash stuck in orders that slipped.
Lines at risk | 2 |  | Confirm these ship dates this week.
Lines with a silent supplier (stale) | 1 |  | No update for longer than your stale threshold.
Lines that run out of stock before the ETA | 3 |  | Stockouts coming unless the order arrives early or you top up.
Follow-ups due today or earlier | 5 |  | Count of lines whose follow-up date has arrived.
Average days late (late lines) | 3.5 |  | How far past the ETA your late orders are.
Average days since last update (open lines) | 5.7 |  | How long suppliers typically go quiet.
Lines by health | Lines | Value ($)
Late | 2 | 10600
Ship overdue | 2 | 9000
At risk | 2 | 12600
Stale | 1 | 3300
On track | 3 | 10550
Closed | 2 | 6800
To see the lines behind a number, open Open POs and filter the Health column.

## Supplier scorecard
Supplier scorecard
Type each supplier name in column A exactly as in Open POs. The sample names below can be overwritten.
Supplier | Open lines | Late | Ship overdue | At risk | Open value ($) | Avg days late | Longest silence (days) | % of open lines late or overdue
Supplier A - Ningbo (sample) | 3 | 1 | 1 | 0 | 13050 | 5 | 10 | 66.67%
Supplier B - Shenzhen (sample) | 3 | 1 | 0 | 1 | 11400 | 2 | 12 | 33.33%
Supplier C - Yiwu (sample) | 2 | 0 | 1 | 0 | 8400 | 0 | 11 | 50%
Supplier D - Dongguan (sample) | 2 | 0 | 0 | 1 | 13200 | 0 | 2 | 0%

## Follow-up templates
Follow-up templates
Pick the row that matches the line's Health, fill the {brackets}, and send by email, WeChat or WhatsApp. Review before sending.
Use when Health is | English | Simplified Chinese
Stale | Hi {Name}, could you share the current status of PO {PO #} ({Item})? Please confirm the ship date, and send a few photos if production is finished. Thank you! | 您好 {Name}，请问订单 {PO #}（{Item}）目前的进度如何？请确认发货日期，如果已经生产完成，请发几张照片。谢谢！
At risk | Hi {Name}, just confirming that PO {PO #} is still on track to ship on {Ship date}. Is there anything that could cause a delay? | 您好 {Name}，想确认一下订单 {PO #} 是否仍按计划在 {Ship date} 发货？有没有可能导致延误的情况？
Ship overdue | Hi {Name}, PO {PO #} was due to ship on {Ship date}, and we haven't received shipping details yet. What is the new ship date, and what is causing the delay? We need a firm date by {Deadline}. | 您好 {Name}，订单 {PO #} 原定于 {Ship date} 发货，但我们还没有收到发货信息。请问新的发货日期是什么时候？延误的原因是什么？请在 {Deadline} 前给我们一个确定的日期。
Late | Hi {Name}, PO {PO #} was due to arrive on {ETA} and is now {Days late} days late. Please send the tracking number and the updated arrival date today. This delay affects our stock, so a quick reply would help a lot. | 您好 {Name}，订单 {PO #} 原定于 {ETA} 到货，现在已经延迟 {Days late} 天。请今天发给我们物流单号和最新的到货日期。这次延误影响了我们的库存，请尽快回复，非常感谢。
Tip | Suppliers on WeChat usually answer faster there than by email. Paste the Chinese version and attach the PO number.